## 000-S-TBE-60002-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Ravi Kumar | ALL OWNER COMMENTS IN THIS TBE TO BE REPLIED, AGREED AND CONCLUSIONS INCLUDED IN TBE PRIOR TO LOA.
2 | Text Box | 2 | MAK | General Comment: This is not the latest document template. For all documents, use the latest document template that is part of the Homogenisation Procedure.
3 | Call-out | 4 | Ravi Kumar | ONLY FILTREX AND RONNINGEN-PETTER WERE IN 'A' CATEOGRY OF BIDDERS LIST. INCLUDE THE BID HISTORY OF RONNINGEN-PETTER IN SECTION 2.2 - WAS THE BID ISSUED? OFFER NOT SUBMITTED BY BIDDER?
4 | Call-out | 4 | Ravi Kumar | MAHLE IS ON ADDITIONAL SUBCONTRACTOR LIST SUBJECT TO LICENSOR APPROVAL. IN THE EVENT MAHLE IS SELECTED THE PQ EXERCISE IS REQD TO BE COMPLETED INCLUDING LICENSOR APPROVAL
5 | Call-out | 4 | Ravi Kumar | BEA IS IN 'N' CATEGORY OF BIDDERS LIST. IN THE EVENT BEA IS SELECTED THE PQ EXERCISE IS REQD TO BE COMPLETED INCLUDING LICENSOR APPROVAL
6 | Text Box | 10 | MAK | 2018-01-02
7 | Cloud+ | 10 | MAK | Change to Bapco Doc. No. on all pages
8 | Text Box | 10 | MAK | Indicate Attachment 1
9 | Text Box | 11 | MAK | 2018-02-02
10 | Text Box | 13 | Ali Kadhem | As stated in the 3HDU Feed Filter 021U0001 datasheet, the maximum flux rate of 18 GPM/ft2 must be achieved all the time i.e. during normal operation and when one vessel/bank of vessels/housing is taken out of service for maintenance. Any deviation from this requirement is not acceptable.
11 | Text Box | 13 | MAK | Indicate Attachment 2
12 | Cloud+ | 13 | MAK | Change to Bapco Doc. No. on all pages
13 | Text Box | 16 | MAK | Indicate Attachment 3
14 | Text Box | 16 | Ali Kadhem | As stated in the 3HDU Feed Filter 021U0001 datasheet, the maximum flux rate of 18 GPM/ft2 must be achieved all the time i.e. during normal operation and when one vessel/bank of vessels/housing is taken out of service for maintenance. Any deviation from this requirement is not acceptable.
15 | Text Box | 18 | Ali Kadhem | As stated in the 3HDU Feed Filter 021U0001 datasheet, the maximum flux rate of 18 GPM/ft2 must be achieved all the time i.e. during normal operation and when one vessel/bank of vessels/housing is taken out of service for maintenance. Any deviation from this requirement is not acceptable.
16 | Text Box | 18 | MAK | Indicate Attachment 4
17 | Text Box | 20 | MAK | Indicate Attachment 5
18 | Text Box | 20 | MAK | Add Bapco Doc. No. on all pages
19 | Text Box | 25 | MAK | Add Bapco Doc. No. on all pages
20 | Text Box | 25 | MAK | Indicate Attachment 6
21 | Text Box | 30 | MAK | Add Bapco Doc. No. on all pages
22 | Text Box | 30 | MAK | Indicate Attachment 7