## 000-S-TBE-60008-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 2 | MAK | General Comment: This is not the latest document template. For all documents, use the latest document template that is part of the Homogenisation Procedure.
2 | Text Box | 3 | MAK | S
3 | Callout | 4 | David.Jimenez | e
4 | Callout | 4 | David.Jimenez | Final negotiation is different from technical clarification and comes at a later stage Please state whether technical clarifications have been carried out or not and whether the vendor has rejected to participate in technical clarifications or not
5 | Call-out | 5 | Ravi Kumar | IDEALLY TBE SHOULD BE ISSUED AFTER ALL POINT WITH VENDORS ARE CLOSED. HOWEVER, IT IS EXPECTED THAT THE OPEN ITEMS AS LISTED UNDER SECTION 3 SHOULD BE CLOSED IN COMPLIANCE WITH MR AND BMPS. ANY DEVIATIONS SHOULD BE BROUGHT TO NOTICE OF OWNER
6 | Text Box | 5 | Francis L | PLC control shall be provided.
7 | Callout | 6 | David.Jimenez | e
8 | Text Box | 6 | David.Jimenez | Please give also a summary of the most critical issues identified leading to non technical acceptability, if any
9 | Text Box | 6 | MAK | S
10 | Text Box | 7 | Ali Kadhem | As discussed, this is the first Licensed Package TBE received by the Owner. Since this is a licensed package and the Owner will acquire this technology, it is expected that the Owner and Technology Supplier (Linde or UOP) will be required to enter into various agreement e.g. License Agreement, Guarantee Agreement, PSA Adsorbent Supply Agreement and Equipment supply Agreement. TTSJV to review internally and advise the steps leading to the procurement of such licensed package items. Such Agreements can then be novated to TTSJV for the EPC of work package in line with other Licensed Process Units. This approach can be agreed between Bapco and TTSJV, developed into a procedure and then applied to other Licensed packages e.g. (but not limited to) LPG Mercaptan Removal package, LPG Olefin Saturation Package, Spent Caustic Treating Unit etc.
11 | Text Box | 7 | Ali Kadhem | As mentioned in the Design Specification Sheet for the PSA, in the “Performance Guarantees” section, TTSJV to request UOP and LINDE to fill the table provided in Attachment 2 (file is attached ).
12 | Cloud+ | 7 | MAK | Change on all pages to Bapco Doc. No.:
13 | Text Box | 7 | Ravi Kumar | IT IS NOTED IN LINDE'S OFFER THAT THE SOUND LEVEL EXCEEDS THE LIMITS OF BMPS REQUIREMENTS OF 82 DBA. HOWEVER, IT NOT LISTED IN THE DEVIATION LIST OF TBE. TTSJV TO NOTE THAT ANYTHING NOT SPECIFICALLY LISTED IN DEVIATIONS, IT WILL BE CONSIDERED IN COMPLIANCE WITH ITB
14 | Text Box | 7 | Ali Kadhem | It is noted in the LINDE proposal (section 3.3) the tail gas temperature is approximately 83ºC. TTSJV to request LINDE to confirm that the temperature of 83 is ºF (not ºC), as the maximum temperature for the tail gas shall be 90ºF.
15 | Text Box | 7 | Ali Kadhem | It is noted that, the nitrogen specification required by LINDE and UOP are different than the nitrogen composition for the new nitrogen unit specified in the BMPS-A1. TTSJV to request UOP and LINDE to confirm that the nitrogen composition as per BMPS-A1 is acceptable.
16 | Text Box | 7 | Ali Kadhem | LINDE’s H2 product quality shows C2H6 content of 30 vppm and C3H8 content of 20 vppm. Therefore, LINDE product quality is not meeting the required spec. As stated in the Design Specification Sheet for the PSA, the product hydrogen specification is 99.9 mol% min hydrogen and 0.1 mol% max of impurities (CH4 + N2), thus we do not expect any other impurities. Therefore, this deviation is not acceptable. TTSJV to request LINDE the following: a.To confirm that the required specifications can be met and guaranteed. b.Advise what changes are required to their current configuration/design to meet the product hydrogen specifications.
17 | Text Box | 7 | Ali Kadhem | TTSJV to request UOP and LINDE to fill the table provided in Attachment 1 (file is attached ). This is required for technical evaluation of the proposals.
18 | Call-out | 8 | Ravi Kumar | THIS IS A DEVIATION TO THE SPEC REQUIREMENT. NOT ACCEPTABLE
19 | Text Box | 9 | Omran A | (Processor, Power module & Communication)
20 | Callout | 9 | Francis L | Engineering workstation (desktop) is required. This is in addition to laptop and operator interface on PLC cabinet door at front.
21 | Text Box | 9 | Ahmed Bucheeri | Forgings and piping material to be confirmed
22 | Text Box | 9 | Ahmed Habib | Laptop specification shall comply with BMPS-J01 section 7
23 | Callout | 9 | Francis L | Laptop to be supplied and shall be in addition to an operator interface (with graphics displays) on the PLC cabinet door. Laptop to be set up and complete with relevant application to to connect to PLCs.
24 | Callout | 9 | Francis L | Manufacturers shall be as per AVL
25 | Callout | 9 | Francis L | Not on AVL. (Rockwell-AB, Schneider or Siemens on AVL)
26 | Callout | 9 | Francis L | PLC to be fully configured and supplied by vendor.
27 | Call-out | 9 | Bachir M | Redundant : meaning 2 PLCs or redundant modules within one PLC ? to be clarified
28 | Text Box | 9 | Ahmed Bucheeri | To confirm the compliance with the requirements.
29 | Call-out | 9 | Ahmed Bucheeri | Tracing shall be by steam as per BMPS-L2
30 | Text Box | 11 | MAK | Indicate Attachment 2 (000-S-TBE-60008-001) on all related pages
31 | Call-out | 11 | Ravi Kumar | SEAT LEAKAGE TEST IS REQUIRED. DEVIATION IS NOT ACCEPTABLE
32 | Call-out | 12 | Ravi Kumar | CONTRACT AVL REQUIREMENTS SHOULD BE MET FOR MATERIALS SOURCED FROM CHINA OR VENDORS NOT IN APPROVED VENDOR LIST
33 | Call-out | 12 | Ravi Kumar | SHOULD BE FIRE-SAFE
34 | Text Box | 12 | Ahmed Bucheeri | This deviation is not accepted. This service is considered a Hydrogen service as per BMPS-A3 clause 7.3,
35 | Text Box | 12 | Ahmed Bucheeri | This deviation is not accepted. This service is wet H2S service and it shall comply with BMPS-A26 & NACE MR0103
36 | Text Box | 12 | Ahmed Bucheeri | This proposal is rejected. Aluminium jacketing is not allowed, refer to BMPS-N1, 6.6
37 | Call-out | 14 | Rashed Almudahka | BIDDER's deviation is not acceptable. BIDDER to provide two manways and ensure full compliance to BMPS-A3.
38 | Call-out | 14 | Ahmed Bucheeri | Details to be provided
39 | Text Box | 14 | MAK | Indicate Attachment 3 (000-S-TBE-60008-001) on all related pages
40 | Call-out | 15 | Ravi Kumar | CONTRACT AVL PQ REQUIREMENTS SHALL BE FOLLOWED FOR VENDORS NOT IN THE AVL
41 | Text Box | 15 | Ahmed Bucheeri | Deviation is rejected.
42 | Call-out | 15 | Ravi Kumar | THE EXPLANATION IS NOT A VALID JUSTIFICATION FOR DEVIATION. BIDDER TO COMPLY WITH BMPS
43 | Call-out | 17 | Ahmed Bucheeri | To provide details of vendor piping classes