## 005-A-EQL-55001-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | hyunjin.paeng | Following Typical Comments shall be reflected in Equipment list in all units : - Pump position to be indicated ( H or V ) - Pump Casing material to be indicated in External column
2 | Text Box | 1 | Dowon Pyun | To consider general comments shown in document no. 098-A-EQL-00001-001 whatever applicable
3 | Text Box | 1 | seongjin.lee | The transmittal is approved as code 2 on condition that all the comments on this transmittal and general & typical comments on the Item Index for all units shall be incorporated and closed to the satisfaction of Owner in next revision.
4 | Callout | 2 | hyunjin.paeng | Pumps to be added
5 | Callout | 3 | hyunjin.paeng | Pump Casing material to be indicated in External column
6 | Text Box | 3 | Aamer.Hubail | General Comment: Change all PM to M
7 | Cloud+ | 3 | Aamer.Hubail | There is no Tag no. PM. Change to M