## 005-A-PID-00001-001-R9A-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | Page 1 | MAK | Change to P&ID on all sheets
2 | Text Box | Page 1 | Basheer.isa | general comment: the instrument identification to be as per the latest legand.
3 | Text Box | Page 1 | Basheer.isa | move the low alarm to the right
4 | Text Box | Page 1 | Mahdi Ali | BAPCO LEGACY DRAWING NO. BRA058520 SHEET 1 ADD THE ABOVE NOTE BELOW THE DRAWING NUMBER AS WAS ORIGINALLY PROVIDED BY BAPCO. DO NOT REMOVE THIS NOTE FROM ALL THE PID PROVIDED BY BAPCO
5 | Callout | Page 1 | Mahdi Ali | CHANGE DOCUMENT NUMBER TO '005-A-PID-00005-001' AS PER BAPCO DOCUMENT MANAGEMENT SYSTEM. CHANGE OPCs ACCORDINGLY AND ALL REFERENCES TO THIS DRAWING
6 | Callout | Page 1 | Mahdi Ali | REVISION PROVIDED BY BAPCO WAS '8A' THUS THIS DRAWING SHALL HOLD REVISION ''8B'
7 | Callout | Page 1 | Mahdi Ali | RETAIN EXISTING INFORMATION. THE '62756 AND EN0815 SHALL BE INSERTED IN BAPCO REVISION BOX FOR THE FINAL HANDOVER. THIS NOTE APPLIED TO ALL BAPCO EXISTING DRAWINGS
8 | Callout | Page 1 | A Albalooshi | General Comment: The tie-in list shall be provided for BAPCO review and approval. The EPC contractor shall provide a detailed shutdown list in a sequential manner proposing the location without jeopardizing the operation and safety of the units.
9 | Call-out | Page 1 | Ali Hasan | - -This line is connected to FCC/South flares header as shown in sheet 4. Please modify the line description. -3"-V017 is connected to FCC/Remote flare. However, our understanding that this line will not be used because vent to flare (FCC or South) will