## 005-A-PID-00003-001-R8A-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | Page 1 | Omran A | Enraf Tank Gauging and Management System
2 | Text Box | Page 1 | Mahdi Ali | BAPCO LEGACY DRAWING NO. BRA058518 SHEET 1 ADD THE ABOVE NOTE BELOW THE DRAWING NUMBER AS WAS ORIGINALLY PROVIDED BY BAPCO. DO NOT REMOVE THIS NOTE FROM ALL THE PID PROVIDED BY BAPCO
3 | Callout | Page 1 | Mahdi Ali | REVISION PROVIDED BY BAPCO WAS '7' THUS THIS DRAWING SHALL HOLD REVISION ''7A'
4 | Callout | Page 1 | Mahdi Ali | RETAIN EXISTING INFORMATION. THE '62756 AND EN0815 SHALL BE INSERTED IN BAPCO REVISION BOX FOR THE FINAL HANDOVER. THIS NOTE APPLIED TO ALL BAPCO EXISTING DRAWINGS
5 | Callout | Page 1 | Mahdi Ali | SOURCE DRAWNG NUMBER TO CHANGE AS COMMENTED ON 005-A-PID-00001-001
6 | Call-out | Page 1 | Ali Hasan | Ball valve to be used in LPG service according to the project spec. This is general item. Please review/modify all valves in LPG service.