## 005-A-PID-00004-001-R9A-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | Page 1 | Mahdi Ali | BAPCO LEGACY DRAWING NO. BRA058519 SHEET 1 ADD THE ABOVE NOTE BELOW THE DRAWING NUMBER AS WAS ORIGINALLY PROVIDED BY BAPCO. DO NOT REMOVE THIS NOTE FROM ALL THE PID PROVIDED BY BAPCO
2 | Callout | Page 1 | Mahdi Ali | REVISION PROVIDED BY BAPCO WAS '8' THUS THIS DRAWING SHALL HOLD REVISION ''8A'
3 | Callout | Page 1 | Mahdi Ali | RETAIN EXISTING INFORMATION. THE '62756 AND EN0815 SHALL BE INSERTED IN BAPCO REVISION BOX FOR THE FINAL HANDOVER. THIS NOTE APPLIED TO ALL BAPCO EXISTING DRAWINGS
4 | Callout | Page 1 | Mahdi Ali | SOURCE DRAWNG NUMBER TO CHANGE AS COMMENTED ON 005-A-PID-00001-001
5 | Call-out | Page 1 | Edgardo | Please indicate the unit numbers at this B/L