## 005-G-DAT-00001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Julio.Aguilar | Ensure the use of the project finalized cover page for the all data sheets. | Noted. | Y
2 | Text Box | 1 | seongjin.lee | The document is approved as Code 2 subject to incorporation of information obtained during subsequent detailed engineering development. Prior to issue of the PO the datasheet shall include all the updated details and be in code 2 approval status. | Noted. | Y
3 | Cloud+ | 2 | Julio.Aguilar | Confirm this NPSHa value | NPSHa has been confirmed based on hydraulic calculation result. | Y
4 | Cloud+ | 2 | Julio.Aguilar | Confirm whether the pump autostart is required or manual start. | Manual start is confirmed and updated in Datasheet. | Y
5 | Callout | 2 | Julio.Aguilar | Final figures shall be updated when the final hydraulic calculation is finalized. | Noted. | Y
6 | Callout | 2 | Salman Jaffer | Please refer to Bid Query T1969 and revised as necessary | Refering to T1969, discharge pressure and head had already revised based on hydraulic calculation result. | Y
7 | Callout | 2 | Julio.Aguilar | Remove prefix f | Removed. | Y
8 | Text Box | 2 | hyunjin.paeng | Vertical Pump length shall be determined by vendor referring to NPSHa at Suction Flange. | Noted. | Y
9 | Text Box | 3 | Aamer.Hubail | S-1 (LCB) ref API610 + bid query T583 | Material for casing corrected to "LTCS". | Y
10 | Cloud+ | 5 | Saeed Taher | Type of inspections shall be as per applicable codes. Applicable to all pumps data sheets | It will be marked later as per inspection level. Type of inspections were deleted. | Y
11 | Text Box | 6 | hyunjin.paeng | Vertical Pump length shall be determined by vendor | Noted. | Y
12 | Callout | 8 | Julio.Aguilar | Add: "Refer to project specification BMPS-S6 and BMPS-G2" | Added to note 9. | Y
13 | Cloud+ | 8 | Julio.Aguilar | Note 13 statement shall be consistent with NPSHa value. See further details Refer BMPS-G2 and BMPS-S6. | As per BMPS-G2 Para 8.3.4.3, NPSH margin will be considered. | Y
14 | Text Box | 8 | Salman Jaffer | The following to be provided for the pump: *A logic trips the pumps in case of low-low pressure / low-low level in suction bullet and in case of emergency push button and in case of high-high level on existing Horton sphere. * ervissive to start facility. * START/STOP on the pump, on a local panel and emergency stop at 50ft | All the required logic shall be incorporated on P&ID and C&E diagram, instead of pump data sheet. | Y