## 005-G-DAT-00002-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Julio.Aguilar | Ensure the use of the project finalized cover page for the all data sheets.
2 | Text Box | 1 | seongjin.lee | The document is approved as Code 2 subject to incorporation of information obtained during subsequent detailed engineering development. Prior to issue of the PO the datasheet shall include all the updated details and be in code 2 approval status.
3 | Cloud+ | 2 | Julio.Aguilar | Confirm this NPSHa value
4 | Cloud+ | 2 | Julio.Aguilar | Confirm whether the pump autostart is required or manual start.
5 | Callout | 2 | Julio.Aguilar | Final figures shall be updated when the final hydraulic calculation is finalized.
6 | Cloud+ | 2 | Julio.Aguilar | Flow rate to be confirmed based on the final design of SGPs
7 | Callout | 2 | Julio.Aguilar | Remove prefix f
8 | Text Box | 3 | Aamer.Hubail | S-1 (LCB) ref API610 + bid query T583
9 | Callout | 8 | Julio.Aguilar | Add: "Refer to project specification BMPS-S6 and BMPS-G2"
10 | Cloud+ | 8 | Julio.Aguilar | Note 13 statement shall be consistent with NPSHa value. See further details Refer BMPS-G2 and BMPS-S6.