## 018-A-PID-00008-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Abdul Majeed | DP
2 | Text Box | 1 | Ahmed Habib | General Comment: for all XHS block for E.M. STOP Shall be using "D" suffix. Refer to SPI Database Creation Guidelines
3 | Text Box | 1 | Ahmed Habib | General Comement: for all XHS block used for LOCAL START/STO, suffix "B" shall be used. Refer to SPI Database Creation Guidelines.
4 | Text Box | 1 | rob.urban | ALL ADDITIONAL COMMENTS TO BE DISCUSSED AND MARKED UP AS REQUIRED ON THE MASTER SET DURING JOINT P&ID REVIEW SESSION
5 | Text Box | 1 | Ahmed Habib | Temperature Element and temperature Indicator Loop number is required
6 | Text Box | 1 | Abdul Majeed | Asset No. missing