## 018-A-PID-00010-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Mahdi Ali | Tag number for the driver for pumps shall be inserted on all PIDs as per BMPS-A8 section 8.4.3
2 | Text Box | 1 | Ahmed Habib | Typical: No Suffix shall be used for DCS block. Hence "D" shall be removed.
3 | Text Box | 1 | rob.urban | ALL ADDITIONAL COMMENTS TO BE DISCUSSED AND MARKED UP AS REQUIRED ON THE MASTER SET DURING JOINT P&ID REVIEW SESSION