## 018-A-PID-00023-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Ahmed Habib | Suffix"D" shall be used for EM CLOSE
2 | Text Box | 1 | rob.urban | ALL ADDITIONAL COMMENTS TO BE DISCUSSED AND MARKED UP AS REQUIRED ON THE MASTER SET DURING JOINT P&ID REVIEW SESSION
3 | Text Box | 1 | Abdul Majeed | DP
4 | Text Box | 1 | Abdul Majeed | DP