## 018-A-PID-20002-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Mahdi Ali | INCORRECT IDENTIFICATION FOR THE PURGE CONNECTION TYPE. REFER TO BMPS-A-50003 FOR CORRECT TYPES. THIS APPLIES TO ALL PIDS
2 | Text Box | 1 | Mahdi Ali | Tag number for the driver for pumps shall be inserted on all PIDs as per BMPS-A8 section 8.4.3
3 | Text Box | 1 | Ahmed Habib | Typical for all Centers: No suffix for all DCS block related to current or speed indicator
4 | Text Box | 1 | Ahmed Habib | Typical: For all E.M. CLOSE, suffix "D" shall be used.
5 | Call-out | 1 | Mahdi Ali | Use the updated line type for the fieldbus signals
6 | Text Box | 1 | rob.urban | ANY COMMENTS WILL BE DISCUSSED AND MARKED UP AS REQUIRED DURING THE JOINT P&ID REVIEW SESSIONS