## 018-A-PID-20021-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | rob.urban | ANY COMMENTS WILL BE DISCUSSED AND MARKED UP AS REQUIRED DURING THE JOINT P&ID REVIEW SESSIONS
2 | Text Box | 1 | Mahdi Ali | SHOW INSTRUMENTATION SIMILAR TO 018-A-PID-00020-001
3 | Text Box | 1 | Mahdi Ali | Tag number for the driver for the compressor shall be inserted on all PIDs as per BMPS-A8 section 8.4.3