## 018-A-PID-20022-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | AliRedha Malalla | Pulsation dampers to be givesn Asset Number post equipment selesction.
2 | Text Box | 1 | Mahdi Ali | GENERAL COMMENT TO BE APPLIED TO ALL P&IDS: AS PER BMPS-A8, SECTION 8.4.3, DRIVERS TAG NOS. E.G. MOTORS/TURBINES SHALL ALWAYS BE INSERTED IN ALL P&IDS AND PLACED BELOW THE PARENT EQUIPMENT NO. E.G. PUMP/FAN/MIXER/COOLER WHERE POSSIBLE.
3 | Text Box | 1 | Ahmed Habib | Tag assosciated to DCS shall be with no suffix
4 | Call-out | 1 | Mahdi Ali | USE UPDATED LINE TYPE FOR FIELDBUS
5 | Text Box | 1 | rob.urban | ANY COMMENST WILL BE DISCUSSED AND MARKED UP AS REQUIRED DURING JOINT P&ID REVIEW SESSIONS