## 018-A-STS-00001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Rashed Almudahka | JV to confirm that equipment criticality level is driving its inspection level.
2 | Text Box | 1 | Rashed Almudahka | Revise the list as there are several ones not included e.g. 018E2001, 018E2003, etc.
3 | Callout | 1 | Mahdi Ali | THIS DOCUMENT IS A CALCULATION SHEET AND NOT A STUDY. THUS THE DOCUMENT TYPE SHALL BE 'CAL' AND NOT 'STS'. CHANGE ALL THE REFERENCES TO THIS DOCUMENT ACCORDIGNLY. HOWEVER, IF THIS DOCUMENT IS A STUDY THEN THE TITLE SHOULD BE CHANGED ACCORDINGLY.
4 | Call-out | 2 | Rashed Almudahka | JV to provide the rational of giving 3 as a rating for manufacturing phase of 018C0003 vacuum column and 5 for 018C1003 & 018C2003 train1&2 HP amine absorber and wash column.
5 | Call-out | 2 | Ebrahim | Criticality Rating to be defined
6 | Call-out | 2 | Ebrahim | Bases of the given values need to be defined or shall be referenced to a document
7 | Call-out | 2 | Ebrahim | Motors are not listed?!
8 | Call-out | 2 | Rashed Almudahka | column
9 | Call-out | 2 | Ebrahim | Do not use short form of description. Typical
10 | Call-out | 3 | Rashed Almudahka | JV to revise and confirm this value
11 | Call-out | 3 | Rashed Almudahka | JV to revise and confirm this value
12 | Call-out | 3 | Rashed Almudahka | JV to revise and confirm this value
13 | Call-out | 4 | Rashed Almudahka | JV to revise and confirm this value
14 | Call-out | 4 | Rashed Almudahka | JV to revise and confirm this value
15 | Call-out | 4 | Rashed Almudahka | JV to revise and confirm this value
16 | Call-out | 4 | Rashed Almudahka | JV to revise and confirm this value
17 | Call-out | 5 | Rashed Almudahka | JV to revise and confirm this value
18 | Call-out | 6 | Rashed Almudahka | JV to revise and confirm this value
19 | Call-out | 6 | Rashed Almudahka | JV to revise and confirm this value
20 | Typewritten Text | 7 | steven.coyne | add ref: Criticality Procedure 000-A-PRO-50017-001
21 | Call-out | 7 | Rashed Almudahka | JV to revise and confirm this value