## 018-C-DAT-00001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Mahdi Ali | This datasheet template was revised and will be issued with the Homogenization Procedure. In the next revision, the revised template shall be used.
2 | Callout | 3 | Fatema Hashem | CLARIFY NOTE 7: HOLD UP TIME CALCULATION IS BASED ON VOLUME BETWEEN WHAT LEVELS?
3 | Call-out | 4 | Rashed Almudahka | As per EDP, the vessel elevation shall be based on P1818A/B NPSHR. please confirm its fulfilling the same.
4 | Call-out | 7 | Rashed Almudahka | As per P&ID, vent nozzle is 2". Please clarify
5 | Callout | 10 | Fatema Hashem | ENSURE THIS DATA IS CONSISTENT WITH H&MB