## 018-C-DAT-00003-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 3 | Rashed Almudahka | Integral cladding shall be marked for this Vessel.
2 | Callout | 4 | Fatema Hashem | IMPROVE THE QUALITY OF THIS DRAWING AND ENSURE THAT NOTES ARE PLACES IN THE RELEVANT LOCATION
3 | Call-out | 7 | Rashed Almudahka | Both nozzles are shown in the P&ID as 3". please clarify.
4 | Callout | 8 | Fatema Hashem | BAD QUALITY. IMPROVE