## 018-C-DAT-00004-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 2 | Ahmed Bucheeri | As per attached CLG specification (See 5.2 & 5.3 at pafe 12/26 of this Doc.) fixed internals shall be 2 1/4 Cr-1 Mo. To Confirm.
2 | Text Box | 2 | rob.urban | Cyclical service (high, low pressure), thermal cycling
3 | Text Box | 2 | Ahmed Bucheeri | It includes hydrogen and catalyst. Note 8 to be provided, since is not included in the sheet
4 | Call-out | 3 | Ahmed Bucheeri | Basis feed sheet WOL is required if H2 and H2S exceeds 1965 and 140 PSIG. Further clarification to be provided.
5 | Callout | 3 | Fatema Hashem | Licensor
6 | Callout | 5 | Fatema Hashem | These drawings are not legible. improve quality
7 | Callout | 19 | Fatema Hashem | temperature cannot be 3655. correct