## 018-C-DAT-00006-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 2 | rob.urban | coking service
2 | Callout | 3 | rob.urban | Note 8 appears 2 times. to be renumbered.
3 | Callout | 3 | Fatema Hashem | This is not licensor specification. Please include licensor references PVM-SU-50004-H
4 | Callout | 4 | Fatema Hashem | Add note for continuous density detector span per CLG datasheet note 12
5 | Callout | 6 | Fatema Hashem | All references in this datasheet are to density detector source well. clarify why this service is changed to "level" detector source well?
6 | Callout | 6 | Fatema Hashem | Complete note 14 to clarify "surge time is calculated as the volume between (high?) and (low?) liquid level divided by (normal?) flowrate"