## 018-C-DAT-00007-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 3 | Fatema Hashem | This vessel is insulated per CLG
2 | Callout | 4 | Fatema Hashem | add CLG note6: The shell pierce for the bottom level taps should be as close to the bottom tangent line as practical (150mm recommended)
3 | Callout | 4 | Fatema Hashem | Delete vent. Two manways provided and no steam-out requirement. Vents on high pressure vessels to be avoided
4 | Callout | 5 | Fatema Hashem | Complete note 14 to clarify "surge time is calculated as the volume between (high?) and (low?) liquid level divided by (normal?) flowrate"
5 | Callout | 5 | rob.urban | Note 8 appears 2 times to be renumbered