## 018-C-DAT-00024-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Mahdi Ali | THIS DATASHEET TEMPLATE WAS REVISED AND WILL BE ISSUED WITH THE HOMOGENIZATION PROCEDURE. IN THE NEXT REVISION, THE REVISED TEMPLATE AND COVER PAGE SHALL BE USED.
2 | Call-out | 3 | Rashed Almudahka | Provide the basis of removing the insulation requirement.
3 | Callout | 3 | rob.urban | Not acceptable. vessel to be insulated for heat conservation
4 | Callout | 5 | Fatema Hashem | SPECIFY THE WATER HOLD-UP VOLUME IN THE BOOT