## 018-C-DAT-00041-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Danut.Dragan | Please consider the comments on vessel 018V0036 Data-Sheet as equally valid for this Data-Sheet.
2 | Text Box | 2 | Ahmed Bucheeri | As per EDP the spec for CS material is SA 516 GR70. To confirm