## 018-C-DAT-00047-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | AliRedha Malalla | Cover page is for train 1, however spec. sheet is for train 2. Please correct.
2 | Callout | 4 | Danut.Dragan | no
3 | Callout | 4 | Danut.Dragan | please, take nozzle marks and heights dimensions as in DAT-00046
4 | Callout | 5 | Danut.Dragan | Height / Position dimension (mm) - column shall be inserted in the table
5 | Callout | 5 | Danut.Dragan | in "Service" column should also be mentioned if the Instrument belongs to PCS or ESD. Also Instrument Tag can be added
6 | Callout | 5 | rob.urban | Not required here, on mechanical drawing only