## 018-C-DAT-00053-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Mahdi Ali | THIS DATASHEET TEMPLATE WAS REVISED AND WILL BE ISSUED WITH THE HOMOGENIZATION PROCEDURE. IN THE NEXT REVISION, THE REVISED TEMPLATE AND COVER PAGE SHALL BE USED.
2 | Call-out | 2 | Rashed Almudahka | design temperature as per EDP 450F and FEED 410F. clarify inconsistency.
3 | Call-out | 2 | Rashed Almudahka | add (note 11) to removable internals
4 | Callout | 4 | Fatema Hashem | ARE TWO SEPARATE RV NOZZLES REQUIRED? CHECK AND CONFIRM