## 018-C-DAT-00057-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Mahdi Ali | THIS DATASHEET TEMPLATE WAS REVISED AND WILL BE ISSUED WITH THE HOMOGENIZATION PROCEDURE. IN THE NEXT REVISION, THE REVISED TEMPLATE AND COVER PAGE SHALL BE USED.
2 | Callout | 1 | Fatema Hashem | SAME COMMENTS AS 018-C-DAT-00063-001
3 | Text Box | 4 | Rashed Almudahka | TYPICAL COMMENT TO ALL DATA SHEETS Ensure nozzles location consistency between data sheets, GADs and respective P&ID
4 | Text Box | 6 | AliRedha Malalla | Maintenance accessibility to be ensured to internals.