## 018-C-DAT-00069-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Danut.Dragan | please see general comments on DAT-00033 which are applicable
2 | Callout | 2 | Fatema Hashem | ADD NOTE PER BMPS A3 PARA 7.2 AND ENSURE DESIGN TEMPERATURE IS CONSISTENT WITH P&ID
3 | Text Box | 2 | Rashed Almudahka | provide the basis of changing the operating and design parameters.
4 | Call-out | 3 | Rashed Almudahka | insulation for HC shall be reduced to 50mm and not totally removed basis the new parameters.
5 | Callout | 4 | Fatema Hashem | ADVISE THE REASON FOR DELETING INLET NOZZLE DETAILS
6 | Callout | 5 | Fatema Hashem | LIQUID PROPERTIES TO BE SPECIFIED AT OPERATING CONDITIONS
7 | Callout | 5 | Fatema Hashem | MODIFY NOTE TO SPECIFY CLEARLY THAT THE LIQUID HOLD-UP IS CALCULATED BETWEEN HLL-LLL