## 018-C-DAT-00074-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 2 | Rashed Almudahka | H2 partial pressure is 1.5psia as per FEED and equipment GAD. please clarify.
2 | Callout | 2 | Fatema Hashem | NOTE 14
3 | Call-out | 3 | Rashed Almudahka | inlet nozzles size will be defined by equipment vendor. please clarify.
4 | Call-out | 3 | Rashed Almudahka | integral cladding to be marked
5 | Call-out | 3 | Rashed Almudahka | Seismic zone to be reflected as zero (0).
6 | Callout | 4 | Danut.Dragan | full nozzle tag in the bubble
7 | Callout | 5 | Fatema Hashem | MODIFY NOTE TO SPECIFY CLEARLY THAT THE LIQUID HOLD-UP IS CALCULATED BETWEEN HLL-LLL