## 018-C-DAT-00072-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 4 | Danut.Dragan | both elevations should refer to the same TTL
2 | Call-out | 4 | Rashed Almudahka | Ensure nozzles location consistency between GADs, PDS and respective P&ID
3 | Callout | 4 | Danut.Dragan | Instrument Nozzles numbers to be provided
4 | Callout | 5 | Danut.Dragan | Not applicable
5 | Callout | 5 | Fatema Hashem | REVIEW AND CONFIRM THE SG OF THE LIQUID. THIS IS CONDENSATE.