## 018-C-DAT-00073-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 2 | Fatema Hashem | 300F?
2 | Callout | 2 | Fatema Hashem | CORRECT INCONSISTENCIES IN VESSELS SIZED BETWEEN DATASHEETS AND P&IDS
3 | Call-out | 3 | Rashed Almudahka | provide the basis of changing the vessel support from skirt to legs.
4 | Callout | 4 | Danut.Dragan | - other Alarm Levels shall be represented if any (HH, H, L, LL). Please check / confirm
5 | Callout | 4 | Danut.Dragan | LG Nozzles span shall be bigger than the Transmitter range. Please adjust and represent accordingly.
6 | Callout | 5 | Danut.Dragan | add: "... for the same range"
7 | Callout | 5 | Danut.Dragan | defined as LG Nozzles