## 018-C-DAT-00078-001-R0
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 2 | Fatema Hashem | 800DEGF PER MECH DRAWING. REVIEW INCONSISTENCY
2 | Call-out | 2 | Rashed Almudahka | BMPS-C6 to be referred for reactors manufactured from 2.25Cr-1Mo material
3 | Call-out | 2 | Rashed Almudahka | Latest edition of ASME code to be followed
4 | Callout | 2 | Fatema Hashem | REMOVE THE (-)
5 | Callout | 2 | Fatema Hashem | REVIEW THE MAX HYDROGEN PARTIAL PRESSURE PER CLG EDP REACTOR OPERATING CONDITIONS IT IS 2498 PSIA FOR THE DESIGN CASE AND 2500 PSIA FOR THE ALTERNATE CASE
6 | Callout | 3 | Fatema Hashem | DIMENSIONS SHOULD BE FINALISED BEFORE ISSUING THIS DATASHEET FOR PURCHASE
7 | Call-out | 3 | Rashed Almudahka | JV to provide justification to issue the data sheet for purchase while the flange class is not yet confirmed.
8 | Call-out | 3 | Rashed Almudahka | platform, ladders, etc. shall be required for this equipment
9 | Call-out | 3 | Rashed Almudahka | references shall be made to BMPS-C6 instead of BMPS-C2
10 | Call-out | 3 | Rashed Almudahka | references shall be made to BMPS-C6 instead of PVM-SU-5004-H
11 | Call-out | 3 | Rashed Almudahka | Seismic zone shall be marked as zero
12 | Callout | 3 | Fatema Hashem | SPECIFICATION IS "H" ON SHEET 5, REVIEW CONSISTENCY
13 | Callout | 4 | Fatema Hashem | THESE NOZZLES ARE NOT ASSOCIATED WITH THE REACTOR
14 | Text Box | 5 | asantilli | 018C1001R
15 | Text Box | 5 | asantilli | 018C1001R
16 | Text Box | 5 | asantilli | 1.6
17 | Text Box | 5 | asantilli | 2.4
18 | Text Box | 5 | gmariano | Doc.N. 018-C-DAT-00078-001 Rev. 0 Sh. 5 of 14
19 | Callout | 5 | Fatema Hashem | SPECIFICATION IS "I" ON SHEET 5, REVIEW CONSISTENCY
20 | Text Box | 6 | asantilli | 018C1001R
21 | Text Box | 6 | gmariano | Doc.N. 018-C-DAT-00078-001 Rev. 0 Sh. 6 of 14
22 | Text Box | 7 | asantilli | 018C1001R
23 | Text Box | 7 | gmariano | Doc.N. 018-C-DAT-00078-001 Rev. 0 Sh. 7 of 14
24 | Text Box | 8 | asantilli | 018C1001R
25 | Text Box | 8 | gmariano | Doc.N. 018-C-DAT-00078-001 Rev. 0 Sh. 8 of 14
26 | Text Box | 9 | asantilli | 018C1001R
27 | Text Box | 9 | gmariano | Doc.N. 018-C-DAT-00078-001 Rev. 0 Sh. 9 of 14
28 | Text Box | 10 | asantilli | 018C1001R
29 | Text Box | 10 | gmariano | Doc.N. 018-C-DAT-00078-001 Rev. 0 Sh. 10 of 14
30 | Text Box | 11 | asantilli | 018C1001R
31 | Text Box | 11 | gmariano | Doc.N. 018-C-DAT-00078-001 Rev. 0 Sh. 11 of 14
32 | Text Box | 12 | asantilli | 018C1001R
33 | Text Box | 12 | gmariano | Doc.N. 018-C-DAT-00078-001 Rev. 0 Sh. 12 of 14
34 | Text Box | 12 | asantilli | HOLD
35 | Text Box | 13 | asantilli | 018C1001R
36 | Text Box | 13 | gmariano | Doc.N. 018-C-DAT-00078-001 Rev. 0 Sh. 13 of 14
37 | Text Box | 14 | asantilli | 018C1001R
38 | Text Box | 14 | gmariano | Doc.N. 018-C-DAT-00078-001 Rev. 0 Sh. 14 of 14