## 018-C-DAT-00079-001-R0
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 2 | Ahmed Bucheeri | 3.1"
2 | Call-out | 2 | Rashed Almudahka | Note no. 6 referred for internal material is deleted. please clarify.
3 | Call-out | 2 | Rashed Almudahka | Latest ASME edition to be referred.
4 | Call-out | 2 | Ahmed Bucheeri | To be GR2 or H as per CLG drawing
5 | Call-out | 3 | Rashed Almudahka | TYPICAL COMMENT Seismic zone to be marked as "0" zone.
6 | Text Box | 3 | Rashed Almudahka | TYPICAL COMMENT For high pressure vessel fabricated with 2.25Cr & 1 Mo, BMPS-C6 to be followed. please clarify.
7 | Call-out | 4 | Rashed Almudahka | Feed inlet nozzle size is 12" as per P&ID, please clarify. Also, ensure consistency between GAD, PDS & respective P&ID
8 | Text Box | 5 | gcasti | X = 870
9 | Text Box | 5 | gcasti | 3415
10 | Text Box | 5 | asantilli | 3.2
11 | Text Box | 5 | gcasti | 2800
12 | Text Box | 5 | gmariano | Doc.N. 018-C-DAT-00079-001 Rev. 0 Sh. 5 of 10
13 | Text Box | 5 | gcasti | 2800
14 | Text Box | 5 | gcasti | 5550
15 | Text Box | 5 | gcasti | LOW LIQUID LEVEL
16 | Text Box | 5 | gcasti | 200
17 | Text Box | 5 | asantilli | 3.2
18 | Text Box | 5 | gcasti | 200
19 | Text Box | 5 | gcasti | 22.5
20 | Text Box | 5 | asantilli | DELETED
21 | Text Box | 5 | asantilli | 018V2005
22 | Text Box | 5 | asantilli | 3.2
23 | Text Box | 5 | Ahmed Bucheeri | To confirm with CLG weather SA 336 for the shell or the heads
24 | Text Box | 6 | gmariano | Doc.N. 018-C-DAT-00079-001 Rev. 0 Sh. 6 of 10
25 | Text Box | 6 | asantilli | 3.2
26 | Text Box | 6 | asantilli | 018V2005
27 | Text Box | 7 | gmariano | Doc.N. 018-C-DAT-00079-001_0 Rev. 0 Sh. 7 of 10
28 | Text Box | 7 | asantilli | 1.6
29 | Text Box | 7 | asantilli | 0.8
30 | Call-out | 7 | Ahmed Bucheeri | GR 8CA
31 | Text Box | 7 | asantilli | 018V2005
32 | Text Box | 8 | gmariano | Doc.N. 018-C-DAT-00079-001 Rev. 0 Sh. 8 of 10
33 | Text Box | 8 | asantilli | 018V2005
34 | Text Box | 9 | gmariano | Doc.N. 018-C-DAT-00079-001 Rev. 0 Sh. 9 of 10
35 | Text Box | 9 | asantilli | 018V2005
36 | Text Box | 10 | gmariano | Doc.N. 018-C-DAT-00079-001 Rev. 0 Sh. 10 of 10
37 | Text Box | 10 | asantilli | 018V2005