## 018-C-DAT-00090-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | MAK | General Comment: This datasheet template was revised and will be issued with the Homogenization Procedure. In the next revision, the revised template and cover page shall be used.
2 | Cloud+ | 1 | MAK | NO. 1 RESIDUE HYDROCRACKING UNIT
3 | Callout | 2 | Fatema Hashem | NOMINAL
4 | Call-out | 2 | Rashed Almudahka | TYPICAL COMMENT JV to clarify instrumentation requirement for this equipment.
5 | Call-out | 2 | Rashed Almudahka | TYPICAL COMMENT spare parts envisaged for this equipment to be identified.
6 | Call-out | 2 | Rashed Almudahka | TYPICAL COMMENT latest ASME edition to be followed.
7 | Text Box | 3 | AliRedha Malalla | to be checked
8 | Call-out | 3 | Rashed Almudahka | insulation thickness shall conform to BMPS-N1.
9 | Text Box | 3 | Rashed Almudahka | OWNER believes the purpose of deleting note 13, 14, 16 & 17 is due to that they will be covered in MR for filters. JV to confirm the same.