## 018-C-DAT-00092-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ | 1 | MAK | NO. 1 RESIDUE HYDROCRACKING UNIT
2 | Text Box | 1 | MAK | General Comment: This datasheet template was revised and will be issued with the Homogenization Procedure. In the next revision, the revised template and cover page shall be used.
3 | Callout | 2 | Fatema Hashem | ADVISE THE REASON FOR REDUCING THE DESIGN TEMPERATURE FROM 500F TO 250F
4 | Callout | 2 | Fatema Hashem | GENERAL COMMENT: PLEASE REFER TO BMPS-A8 SECTION 4.5.1: DO NOT INDICATE FIGURES IN EUROPEAN STYLE (WHICH USES COMMAS FOR DECIMAL POINTS AND PERIODS FOR THOUSANDS SEPARATORS), USE UK/US STYLE WITH PERIODS FOR DECIMAL PLACES AND COMMAS FOR THOUSANDS SEPARATORS. CHECK AND CORRECT ALL FIGURES
5 | Call-out | 2 | Rashed Almudahka | referred note no.18 is deleted. please clarify.