## 018-C-DAT-00106-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ | 1 | MAK | NO. 1 RESIDUE HYDROCRACKING UNIT
2 | Text Box | 1 | MAK | General Comment: This datasheet template was revised and will be issued with the Homogenization Procedure. In the next revision, the revised template and cover page shall be used.
3 | Call-out | 2 | Ahmed Bucheeri | To be killed CS as per MSD
4 | Call-out | 2 | Rashed Almudahka | provide basis of decreasing the maximum allowable pressure drop from 50psi as per FEED data sheet to 15psi.
5 | Text Box | 3 | Ahmed Bucheeri | To be 100% RT