## 018-C-GAD-00001-001-R0
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Fatema Hashem | 850DEGF PER DATASHEET. REVIEW INCONSISTENCY
2 | Callout | 1 | Danut.Dragan | Please, follow the comments on the GAD-0002, 018C1002R
3 | Call-out | 1 | Ahmed Bucheeri | To add the requirement of impact testing for the CS skirt component as per NOTE No.33 of CLG DRAWING
4 | Call-out | 1 | Rashed Almudahka | TYPICAL COMMENT Ensure consistency between GADs, PDS and respective P&ID