## 018-C-GAD-00002-001-R0
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Danut.Dragan | "PUMP NOZZLE" Contractor to confirm and complete in Nozzle - notes.
2 | Callout | 1 | Danut.Dragan | "RING M" Contractor to confirm and complete in Nozzle - notes.
3 | Callout | 1 | Danut.Dragan | "SKIRT" Contractor to confirm and complete in Nozzle - notes.
4 | Callout | 1 | Fatema Hashem | 850DEGF PER DATASHEET. REVIEW INCONSISTENCY
5 | Callout | 1 | Danut.Dragan | In P&ID is shown a Temperature Sensor (duplex) in Thermo-Well and Clamping Process Connection, which is not listed. Please clarify and adjust accordingly.
6 | Callout | 1 | Danut.Dragan | Process Connection of Nuclear Density Transmitters shall be noted / marked in "Nozzle Schedule" and described in notes.
7 | Callout | 1 | Danut.Dragan | Process Connection of Skin Thermo-Couples shall be specified and described in Notes.
8 | Callout | 1 | Danut.Dragan | Thermo-Couple in Thermo-well,
9 | Call-out | 1 | Ahmed Bucheeri | To add the requirement of impact testing for the CS skirt component as per NOTE No.33 of CLG DRAWING NO. BD-143128-01