## 018-C-GAD-00018-003-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Danut.Dragan | Position of the Detectors should be on the same side with the Nuclear Source Well. Instrument Vendor will decide about final arrangement. - Level figures to be checked and confirmed correct
2 | Callout | 1 | Danut.Dragan | Guide support shall be provided
3 | Text Box | 1 | Mahdi Ali | INCLUDE EQUIPMENT TAG NUMBER IN ALL SHEETS.
4 | Callout | 1 | Fatema Hashem | This drawing is missing several detail drawing related to the catalyst transfer vessels e.g. nozzle details. clarify if these will be in the GAD or kept only as part of datasheet?