## 018-C-GAD-00031-003-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Danut.Dragan | Nozzle projection and horizontal position / dimension shall be specified
2 | Callout | 1 | rob.urban | Vessel ID not shown
3 | Text Box | 1 | Mahdi Ali | INCLUDE EQUIPMENT TAG NUMBER IN ALL SHEETS.
4 | Callout | 1 | Danut.Dragan | Nozzles Projection shall be specified
5 | Callout | 1 | Danut.Dragan | as in Nozzle Sckedule