## 018-C-GAD-00050-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Mahdi Ali | ALL THE TEXT IN THIS DRAWING SHALL SEARCHABLE. TEXT FONTS AND STYLES SHALL BE AS PER BMPS-A8
2 | Call-out | 1 | Rashed Almudahka | Add (w/ inlet baffle) in the note for N1
3 | Call-out | 1 | Rashed Almudahka | vent nozzle mark number is duplicated with steam out one. please modify.
4 | Call-out | 1 | Rashed Almudahka | As per P&ID, vapour outlet line size is 6". please clarify