## 018-C-GAD-00052-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ | 1 | MAK | 3
2 | Cloud+ | 1 | MAK | 018 - NO. 1 RESIDUE HYDROCRACKING UNIT
3 | Call-out | 1 | Rashed Almudahka | Add "w/ vortex breaker" to N3 notes Add "w/ inlet shroud ring" to N1 notes
4 | Call-out | 1 | Rashed Almudahka | As per BMPS-N1, P.P. insulation thickness for mentioned operating temperature shall be 40mm, please clarify
5 | Cloud+ | 1 | MAK | Fill in EX and PN nos.
6 | Text Box | 1 | MAK | General Comment: All the texts in drawings shall be searchable and in UPPERCASE. Text fonts and styles shall be as per BMPS-A8.
7 | Call-out | 1 | Rashed Almudahka | provide the basis of adding N7 to this equipment.
8 | Call-out | 1 | Ahmed Bucheeri | To clarify the selection of dissimilar material for the fixed internal "SS304L" although its mentioned CS in the material list of the data sheet
9 | Call-out | 1 | Rashed Almudahka | TYPICAL COMMENT Check and evaluate consistency across all vessels in 1RHCU - "in providing a ventilation nozzle"