## 018-C-GAD-00054-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ | 1 | MAK | 3
2 | Cloud+ | 1 | MAK | 018 - NO. 1 RESIDUE HYDROCRACKING UNIT
3 | Callout | 1 | Fatema Hashem | ADD PRESSURE AND TEMPERATURE OPERATING RANGE: 10-680PSIG AND 100-445DEGF
4 | Callout | 1 | Danut.Dragan | add: "Nuclear Sources Well" - meant for Density and Level Instruments
5 | Call-out | 1 | Rashed Almudahka | As per BMPS-N1, P.P. insulation thickness for mentioned operating temperature shall be 50mm, please clarify
6 | Call-out | 1 | Ahmed Bucheeri | As per EDP the spec for CS material is SA 516 GR70. To confirm
7 | Cloud+ | 1 | MAK | Fill in EX and PN nos.
8 | Text Box | 1 | MAK | General Comment: All the texts in drawings shall be searchable and in UPPERCASE. Text fonts and styles shall be as per BMPS-A8.
9 | Callout | 1 | Danut.Dragan | Nuclear Instruments: -One Level Switch -One Density Meter -Two Level Transmitters 1. Nozzle tags shall have different numbers, with no prefixes. 2. Service to be adjusted to correspond to the Data-Sheet specific elevation on each instrument. 3. The Drawing sh.3, to be updated accordingly
10 | Callout | 1 | Danut.Dragan | Two nozzles belong to one Level Switch, and one nozzle belongs to a Level Transmitter. Nozzle different numbers to be assigned.