## 018-C-GAD-00055-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ | 1 | MAK | 3
2 | Cloud+ | 1 | MAK | 018 - NO. 1 RESIDUE HYDROCRACKING UNIT
3 | Callout | 1 | Fatema Hashem | ADD PRESSURE AND TEMPERATURE OPERATING RANGE: 10-680PSIG AND 100-445DEGF
4 | Text Box | 1 | Ahmed Bucheeri | As per EDP the spec for CS material is SA 516 GR70. To confirm
5 | Cloud+ | 1 | MAK | Fill in EX and PN nos.
6 | Text Box | 1 | MAK | General Comment: All the texts in drawings shall be searchable and in UPPERCASE. Text fonts and styles shall be as per BMPS-A8.
7 | Callout | 1 | Danut.Dragan | Please, consider the comments done for 018V0036 GA (in the same transmittal), entirely and equally applicable on this GA.