## 018-C-GAD-00057-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ | 1 | MAK | 3
2 | Cloud+ | 1 | MAK | 018 - NO. 1 RESIDUE HYDROCRACKING UNIT
3 | Callout | 1 | Fatema Hashem | ADD PRESSURE AND TEMPERATURE OPERATING RANGE: 10-680PSIG AND 100-445DEGF
4 | Text Box | 1 | Ahmed Bucheeri | As per EDP the spec for CS material is SA 516 GR70. To confirm
5 | Cloud+ | 1 | MAK | Fill in EX and PN nos.
6 | Text Box | 1 | MAK | General Comment: All the texts in drawings shall be searchable and in UPPERCASE. Text fonts and styles shall be as per BMPS-A8.
7 | Callout | 1 | Danut.Dragan | Nuclear Instruments: - One: Level Switch - Two: Level Transmitter - continuous type - One: Density Analyser - point Contractor to check the respective elevations and assign Process Connection no consistent with Drawing
8 | Callout | 1 | Danut.Dragan | Should read: "INTERNAL NUCL. SOURCES WELL FOR LEVEL AND DENSITY METERS" or similar.
9 | Callout | 1 | Danut.Dragan | They are different Instruments and shall be assigned different Nozzle numbers.
10 | Callout | 1 | Danut.Dragan | This nozzle belongs to a different Instrument. It should be marked with different Nozzle no.