## 018-C-GAD-00058-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ | 1 | MAK | 3
2 | Cloud+ | 1 | MAK | 018 - NO. 1 RESIDUE HYDROCRACKING UNIT
3 | Call-out | 1 | Rashed Almudahka | add note no.16 from PDS to M2 nozzle notes
4 | Callout | 1 | Fatema Hashem | ADD PRESSURE OPERATING RANGE: 0.3-680PSIG
5 | Text Box | 1 | Ahmed Bucheeri | As per EDP the spec for CS material is SA 516 GR70. To confirm
6 | Cloud+ | 1 | MAK | Fill in EX and PN nos.
7 | Text Box | 1 | MAK | General Comment: All the texts in drawings shall be searchable and in UPPERCASE. Text fonts and styles shall be as per BMPS-A8.
8 | Callout | 1 | Danut.Dragan | Should read: "INTERNAL NUCL. SOURCES WELL -DENSITY METERS" or similar.
9 | Callout | 1 | Danut.Dragan | They are different Instruments and shall be assigned different Nozzle numbers.