## 018-C-GAD-00066-003-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ | 1 | MAK | 018 - NO. 1 RESIDUE HYDROCRACKING UNIT
2 | Text Box | 1 | MAK | General Comment: All the texts in drawings shall be searchable and in UPPERCASE. Text fonts and styles shall be as per BMPS-A8.
3 | Callout | 1 | Danut.Dragan | Temperature Dual Sensor is shown located at vessel side shell (see the respective P&ID). Contractor to check and confirm.
4 | Call-out | 1 | Rashed Almudahka | Wear plate dimensions to be plotted/ provided