## 018-C-GAD-00067-003-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Mahdi Ali | ALL THE TEXT IN THIS DRAWING SHALL SEARCHABLE. TEXT FONTS AND STYLES SHALL BE AS PER BMPS-A8
2 | Text Box | 1 | Mahdi Ali | INCLUDE EQUIPMENT TAG NUMBER IN ALL SHEETS
3 | Callout | 1 | Danut.Dragan | Orientation view and representation
4 | Callout | 1 | Danut.Dragan | P&ID shows the Instrument Level Nozzles on the Vessel Shell, not on the Vessel Head. Please confirm.