## 018-C-GAD-00068-002-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Mahdi Ali | ALL THE TEXT IN THIS DRAWING SHALL SEARCHABLE. TEXT FONTS AND STYLES SHALL BE AS PER BMPS-A8
2 | Callout | 1 | Fatema Hashem | MODIFY NOTE: LIQUID SPECIFIC GRAVITY OF 1.0 HAS BEEN ASSUMED, NO LIQUID NORMALLY PRESENT.
3 | Text Box | 1 | Rashed Almudahka | Add BMPS-M6 in the reference list
4 | Text Box | 1 | Mahdi Ali | INCLUDE EQUIPMENT TAG NUMBER IN ALL SHEETS