## 018-C-GAD-00072-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Mahdi Ali | UNIT NUMBER SHALL NOT CONTAIN THE AREA CODE
2 | Callout | 1 | Danut.Dragan | GAD general comments: 1. Hight of the Level Instrument Nozzles to be checked and confirmed correct. 2. Each pair of Nozzles (dedicated to one or more Level Instruments as shown in the P&ID) shall have the same and unique Nozzle No. (i.e. N6A/B/C/D should read: N6A/B and N7A/B) 3. No of Nozzle pairs shall be reflected in the Drawing / Orientation as per P&ID. 4. Respective Orientation Angles shall be shown in the relevant section / view, if / where applicable. 5. Nozzle tags to be corrected. i.e.: "7NB" shall read: "N7B", in Nozzle Schedule and Drawing, where applicable. 6. Vessel Equipment Tag No shall be specified on each sheet of the Drawing.
3 | Call-out | 1 | Rashed Almudahka | Design pressure as per EDP is 395psig. please clarify
4 | Callout | 1 | Mahdi Ali | 3
5 | Callout | 1 | Fatema Hashem | REFER TO COMMENTS ON 018V1010