## 018-C-GAD-00084-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ | 1 | MAK | 3
2 | Cloud+ | 1 | MAK | 018 - NO. 1 RESIDUE HYDROCRACKING UNIT
3 | Callout | 1 | Danut.Dragan | definition for LG vs LT Nozzles
4 | Call-out | 1 | Rashed Almudahka | dots to be used instead of commas for numbers' decimal as per BMPS-A8, clause 4.5.1.
5 | Cloud+ | 1 | MAK | Fill in EX and PN nos.
6 | Text Box | 1 | MAK | General Comment: All the texts in drawings shall be searchable and in UPPERCASE. Text fonts and styles shall be as per BMPS-A8.
7 | Callout | 1 | Fatema Hashem | REVIEW AND CONFIRM THE DESIGN TEMPERATURE, EXTERNAL 300F?