## 018-E-DAT-00013-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Rashed Almudahka | TYPICAL COMMENT FOR ALL 1RHCU DATA SHEETS all comments on train 1 data sheets are applicable on train 2 data sheets as well.
2 | Call-out | 3 | Rashed Almudahka | JV to confirm compliance to note 12 of updated EDP data sheet with respect to shell design pressure.
3 | Call-out | 4 | Rashed Almudahka | spec. and grade for tie rods and spacers to be specified
4 | Call-out | 4 | Rashed Almudahka | JV to advise shell cover material
5 | Call-out | 4 | Rashed Almudahka | Channel cover and tube sheet material are different from updated EDP. JV to clarify
6 | Text Box | 8 | Rashed Almudahka | TYPICAL COMMENT FOR ALL DATA SHEETS Licensor data sheets shall not be modified nor edited by JV. It should be attached as a reference to the data sheet.